## To Do
To Do No. | Model No. | Description | Relating to Issue No. | Priority (1 to 5) | Completed?
1 | 1 | Crreate OpenGL application and build a makeshift room |  | 2 | Yes
2 | 1 | Port OpenGL application to JUCE |  | 2 | Yes
3 | 1 | Implement IR generator from Java reflection algorithm |  | 2 | Yes
4 | 1 | Include ability to import model files to replace the makeshift room |  | 4 | No
5 | 1 | Include reflection reverse polarity if able (should make IR oscillate around zero) |  | 3 | Yes
6 | 1 | Get IR generator to write to a file and test effect is what I want when played through a convolution standalone application |  | 2 | Yes
7 | 1 | Implement modification of the IR in real-time |  | 4 | No
8 | 1 | Implement processing of audio and IR by running through a convoluter in real-time |  | 4 | No
9 | 1 | Improve GUI |  | 2 | No
10 | 1 | Add look functionality to OpenGL code with audio pitch and yaw in-line with where listenr is facing |  | 3 | No
11 | 1 | Add pictures to the room in random places to make it look more realistic |  | 4 | No
12 | 1 | Add lighting to the room |  | 2 | No
13 | 1 | Add collision detection |  | 3 | No
14 | 1 | Put ray and listener vectors, and distances in a structure to conserve memory |  | 2 | No
15 | 1 | Allow the camera/listener direction and position be controlled via the keyboard instead of the mouse. This would make processing the IR more stable. |  | 2 | No
16 | 1 | Reference the textures from the 'Assets' folder, not from a fixed location on C drive |  | 3 | Yes
17 | 1 | Write requirements document for what needs finishing |  | 2 | No
18 | 1 | Implement 3D sound engine in IR generator |  | 2 | No
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60

## Issues
Issue No. | Model No. | Description | Proposed fix | Implemented fix | Priority (1 to 5) | Fixed?
1 | 1 | Bricks are going up the left and right walls instead of across | Update the texture vectors for these walls | Done | 3 | Yes
2 | 1 | Textures are not scaling well when different sizes of room are entered |  | Added scaling variable to the texture coordinates | 2 | Yes
3 | 1 | Mouse restricted to app coordinates only. Need coordinated beyond the size of the app window. | Try in a plugin environment. Done, no different. |  | 3 | No
4 | 1 | This method of reflection data gathering is very memory intensive/hungry. Try to find ways of conserving memory or finding methods that use less memory. |  |  | 3 | No
5 | 1 | The number of rays and reflections required is very dependent on the size of the room and positions of the sound source and listener, and it's having a big impact on the amount of memeory required. Find some way of determining how many rays and reflections are required from the available dimensional inputs. | Maybe look at the wave equation. What about scaling the listener box in-line with the size of the room? Would make things more consistent, but is this likely to be a non-linearity? |  | 2 | No
6 | 1 | Some files distort when played through the EasyConvolver plugin and using the current version of the 'output.wav' IR file. |  |  | 3 | No
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50